## Gantt
Work Package |  |  | Start | End | Duration | % Done | Milestone | Ressource | #milestones | #done | #date-diff
HW Concept | Scheduled | Schedule | 2015-09-14 | 2015-09-25 | 10 | [5 empty] | 12
| % done | % done | 2015-09-14 |  |  | 100% |  |  |  | 12
|  | Milestone | 2015-09-27 12:00
Schematic | Scheduled | Schedule | 2015-09-28 | 2015-10-02 | 5 | [5 empty] | 5
| % done | % done | 2015-09-28 |  |  | 100% |  |  |  | 5
|  | Milestone | 2015-10-02 12:00
PCB Layout | Scheduled | Schedule | 2015-10-02 | 2015-10-12 | 7 | [5 empty] | 11
| % done | % done | 2015-10-02 |  |  | 100% |  |  |  | 11
| Milestone | Milestone | 2015-10-12 12:00 |  |  |  | PCB ordered: OK |  | 1
PCB Production | Scheduled | Schedule | 2015-10-13 | 2015-10-15 | 3 | [5 empty] | 3
| Milestone | Milestone | 2015-10-15 12:00 |  |  |  | PCB received:OK |  | 1
PCB -Assembly | Scheduled | Schedule | 2015-10-16 | 2015-10-20 | 3 | [5 empty] | 5
| % done | % done | 2015-10-16 |  |  | 40% |  |  |  | 2
| Milestone | Milestone | 2015-10-20 12:00 |  |  |  | Ready for Test |  | 1
PCB -Test | Scheduled | Schedule | 2015-10-21 | 2015-10-26 | 4 | [5 empty] | 6
| % done | % done
| Milestone | Milestone | 2015-10-26 12:00 |  |  |  | HW-Ready |  | 1
HW Report | Scheduled | Schedule | 2014-09-14 | 2014-10-24 | 31 | [5 empty] | 41
| % done | % done | 2014-09-14 |  |  | 40% |  |  |  | 16.4
| Milestone | Milestone | 2014-10-24 12:00 |  |  |  | HW Report delivered |  | 1

## Help
Hints on using this Gantt-Chart spreadsheet:
This Gantt chart is controlled by eight visible colums, and by three rows (Schedule,%done and Milestone) for a standard entry in the chart. See example below:
Work Package |  |  | Start | End | Duration | % Done | Milestone | Ressource | #milestones | #done | #date-diff
HW Concept | Scheduled | Schedule | 2014-09-15 | 2014-09-26 | 10 | [5 empty] | 12
| % done | % done | 2014-09-15 |  |  | 100% |  |  |  | 12
| Milestone | Milestone | 2014-09-28 12:00 |  |  |  | Ready forTest |  | 1
These cells are directly defined by the user.
These cells are automatically updated.
A fix Start date of a task is directly entered by the user.
If it shall depend on a previous End date, it may be linked to it:
- type "=" into the Start cell and then click into the End cell to which it shall be linked
Ressource cell is just for information and has no impact on the chart.
The textcolors of milestones are manually changed (e.g. from red to green) when a milestone is passed.
If the Milestone cell is empty, no milestone is shown in the chart. If there is any text, a milestone appears with this text associated to it.
To insert / add a new entry, copy the three rows of an existing entry and paste it at the desired position. The chart will automatically be updated.
Modify the cells for the new entry as described above.